## Status Report
Project Status Report Template
Progress against plan, changes, risks, decisions needed, and next period. One screen, one fixed day per week or month.
Header
Project | Period | Owner | Overall (G/A/R)
Website relaunch | W34 | J. Meyer | A
Progress against plan
Workstream | Planned this period | Actual | Trend | Note
Design | Approve final layouts | Approved Tue | up
Content | 12 pages migrated | 7 migrated | down | Two writers pulled to campaign
What changed this period
Change | Impact
Scope: added checkout page | +1 week on content track
Risks and blockers
Risk | Impact | Owner | Mitigation | Status
CMS vendor delay on API access | Content freeze slips | J. Meyer | Escalated to vendor CSM | open
Decisions needed
Decision | Needed from | By when
Approve extra freelance budget (EUR 6k) | COO | Fri
Next period
Item | Owner | Due
Remaining 5 pages migrated | Content team | W35